## Sheet1
1. INITIATION PHASE
Work/Task # & Name: |  | 1.1.1 Define project scope (3 Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) |  | Rate / Day | Rate/Months
1 | Project Manager | 1 | 3 | 306.67 | 920.01 | Project Manager | 306.67 | 9200
| Total Cost (Personnel) For This Work/Task |  |  |  | 920.01 | Back-end Developer | 233.23 | 6997
[6 empty] | Front-end Dveloper | 196.9 | 5907
Work/Task # & Name: |  | 1.1.2 Develop project deliverables (2 Days) |  |  |  | Software Tester | 225 | 6750
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | System Analyst | 183.33 | 5500
1 | Project Manager | 1 | 2 | 306.67 | 613.34 | UI/UX Designer | 186.67 | 5600
| Total Cost (Personnel) For This Work/Task |  |  |  | 613.34 | Database Engineer | 199.87 | 5996
Work/Task # & Name: |  | 1.1.3 Develop project charter (2 Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | Project Manager
1 | Project Manager | 1 | 2 | 306.67 | 613.34 | 3 | 306.67 | 920.01
| Total Cost (Personnel) For This Work/Task |  |  |  | 613.34 | 2 | 306.67 | 613.34
[6 empty] | 2 | 306.67 | 613.34
Work/Task # & Name: |  | 1.2.1 Identify stakeholders (3 Days) |  |  |  | 3 | 306.67 | 920.01
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 4 | 306.67 | 1226.68
1 | Project Manager | 1 | 3 | 306.67 | 920.01 | 2 | 306.67 | 613.34
| Total Cost (Personnel) For This Work/Task |  |  |  | 920.01 | 2 | 306.67 | 613.34
[6 empty] | 1 | 306.67 | 306.67
Work/Task # & Name: |  | 1.2.2 Interview stakeholders (4 Days) |  |  |  | 1 | 306.67 | 306.67
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 3 | 306.67 | 920.01
1 | Project Manager | 1 | 4 | 306.67 | 1226.68 | 6 | 306.67 | 1840.02
2 | System Analyst | 1 | 4 | 183.33 | 733.32 | 2 | 306.67 | 613.34
| Total Cost (Personnel) For This Work/Task |  |  |  | 1960 | 1 | 306.67 | 306.67
[6 empty] | 3 | 306.67 | 920.01
Work/Task # & Name: |  | 1.2.3Document stakeholder requirements (4 Days) |  |  |  | 2 | 306.67 | 613.34
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 3 | 306.67 | 920.01
1 | Project Manager | 1 | 2 | 306.67 | 613.34 | 3 | 306.67 | 920.01
2 | System Analyst | 1 | 2 | 183.33 | 366.66 | 5 | 306.67 | 1533.35
| Total Cost (Personnel) For This Work/Task |  |  |  | 980 | 2 | 306.67 | 613.34
[6 empty] | 1 | 306.67 | 306.67
2. PLANNING PHASE | [5 empty] | 3 | 306.67 | 920.01
[6 empty] | 1 | 306.67 | 306.67
Work/Task # & Name: |  | 2.1.1 Develop Gantt Chart (2 Days) |  |  |  | 5 | 306.67 | 1533.35
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 5 | 306.67 | 1533.35
1 | Project Manager | 1 | 2 | 306.67 | 613.34 |  |  | 19933.55
2 | System Analyst | 1 | 2 | 183.33 | 366.66
| Total Cost (Personnel) For This Work/Task |  |  |  | 980
System Analyst
Work/Task # & Name: |  | 2.1.2 Create WBS(2 Days) |  |  |  | 4 | 183.33 | 733.32
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 2 | 183.33 | 366.66
1 | Project Manager | 1 | 1 | 306.67 | 306.67 | 2 | 183.33 | 366.66
2 | System Analyst | 1 | 2 | 183.33 | 366.66 | 1 | 183.33 | 183.33
| Total Cost (Personnel) For This Work/Task |  |  |  | 673.33 | 2 | 183.33 | 366.66
[6 empty] | 7 | 183.33 | 1283.31
Work/Task # & Name: |  | 2.1.3 Resource planning(1 Days) |  |  |  | 2 | 183.33 | 366.66
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 3 | 183.33 | 549.99
1 | Project Manager | 1 | 1 | 306.67 | 306.67 | 3 | 183.33 | 549.99
2 | System Analyst | 1 | 1 | 183.33 | 183.33 | 3 | 183.33 | 549.99
| Total Cost (Personnel) For This Work/Task |  |  |  | 490 | 4 | 183.33 | 733.32
[6 empty] | 5 | 183.33 | 916.65
Work/Task # & Name: |  | 2.2.1 Identify risks(3 Days) |  |  |  | 10 | 183.33 | 1833.3
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 5 | 183.33 | 916.65
1 | Project Manager | 1 | 3 | 306.67 | 920.01 | 5 | 183.33 | 916.65
2 | System Analyst | 1 | 2 | 183.33 | 366.66 | 5 | 183.33 | 916.65
| Total Cost (Personnel) For This Work/Task |  |  |  | 1286.67 | 3 | 183.33 | 549.99
[6 empty] | 2 | 183.33 | 366.66
Work/Task # & Name: |  | 2.2.2 Develop risk mitigation plan(7 Days) |  |  |  | 2 | 183.33 | 366.66
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 1 | 183.33 | 183.33
1 | Project Manager | 1 | 6 | 306.67 | 1840.02 | 2 | 183.33 | 366.66
2 | System Analyst | 1 | 7 | 183.33 | 1283.31 | 1 | 183.33 | 183.33
| Total Cost (Personnel) For This Work/Task |  |  |  | 3123.33 |  |  | 13566.42
Work/Task # & Name: |  | 2.3.1 Develop communication plan(2 Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | Back-end Developer
1 | Project Manager | 1 | 2 | 306.67 | 613.34 | 5 | 233.23 | 1166.15
2 | System Analyst | 1 | 2 | 183.33 | 366.66 | 20 | 233.23 | 4664.6
| Total Cost (Personnel) For This Work/Task |  |  |  | 980 |  |  | 5830.75
Work/Task # & Name: |  | 2.3.2 Identify communication channels(3 Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | Front-end Developer
1 | Project Manager | 1 | 1 | 306.67 | 306.67 | 21 | 196.9 | 4134.9
2 | System Analyst | 1 | 3 | 183.33 | 549.99 | 15 | 196.9 | 2953.5
| Total Cost (Personnel) For This Work/Task |  |  |  | 856.66 |  |  | 7088.4
Work/Task # & Name: |  | 2.4.1 Define user scope( 3Days) |  |  |  | Database Engineer
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 16 | 199.87 | 3197.92
1 | Project Manager | 1 | 3 | 306.67 | 920.01 | 5 | 199.87 | 999.35
2 | System Analyst | 1 | 3 | 183.33 | 549.99 | 5 | 199.87 | 999.35
| Total Cost (Personnel) For This Work/Task |  |  |  | 1470 | 5 | 199.87 | 999.35
6195.97
Work/Task # & Name: |  | 2.4.2 Define system scope( 3Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | UI/UX Designer
1 | Project Manager | 1 | 2 | 306.67 | 613.34 | 10 | 186.67 | 1866.7
2 | System Analyst | 1 | 3 | 183.33 | 549.99
| Total Cost (Personnel) For This Work/Task |  |  |  | 1163.33
Work/Task # & Name: |  | 2.4.3 Outline exclusions from scope (4Days) |  |  |  | Software Tester
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) | 5 | 225 | 1125
1 | Project Manager | 1 | 3 | 306.67 | 920.01 | 7 | 225 | 1575
2 | System Analyst | 1 | 4 | 183.33 | 733.32 | 3 | 225 | 675
| Total Cost (Personnel) For This Work/Task |  |  |  | 1653.33 |  |  | 3375
3. EXECUTION PHASE
Work/Task # & Name: |  | 3.1.1 Gather requirements(5Days) |  |  |  | 57856.79
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 3 | 306.67 | 920.01
2 | System Analyst | 1 | 5 | 183.33 | 916.65
| Total Cost (Personnel) For This Work/Task |  |  |  | 1836.66
Work/Task # & Name: |  | 3.1.2 Document requirements(10Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 5 | 306.67 | 1533.35
2 | System Analyst | 1 | 10 | 183.33 | 1833.3
| Total Cost (Personnel) For This Work/Task |  |  |  | 3366.65
Work/Task # & Name: |  | 3.2.1 Architectural design(5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | System Analyst | 1 | 5 | 183.33 | 916.65
| Total Cost (Personnel) For This Work/Task |  |  |  | 916.65
Work/Task # & Name: |  | 3.2.2 Database design(16Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Database Engineer | 1 | 16 | 199.87 | 3197.92
| Total Cost (Personnel) For This Work/Task |  |  |  | 3197.92
Work/Task # & Name: |  | 3.2.3 UI/UX design(10Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | UI/ UX Designer | 1 | 10 | 186.67 | 1866.7
| Total Cost (Personnel) For This Work/Task |  |  |  | 1866.7
Work/Task # & Name: |  | 3.3.1 Environment setup(5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Back-end Developer | 1 | 5 | 233.23 | 1166.15
| Total Cost (Personnel) For This Work/Task |  |  |  | 1166.15
Work/Task # & Name: |  | 3.3.2 Front-end development(21Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Front-end Developer | 1 | 21 | 196.9 | 4134.9
| Total Cost (Personnel) For This Work/Task |  |  |  | 4134.9
Work/Task # & Name: |  | 3.3.3 Back-end development(20Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Back-end Developer | 1 | 20 | 233.23 | 4664.6
| Total Cost (Personnel) For This Work/Task |  |  |  | 4664.6
Work/Task # & Name: |  | 3.3.4 Social media integration(15Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Front-end Developer | 1 | 15 | 196.9 | 2953.5
| Total Cost (Personnel) For This Work/Task |  |  |  | 2953.5
Work/Task # & Name: |  | 3.4.1 Integrate with CRM systems(5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Database Engineer | 1 | 5 | 199.87 | 999.35
| Total Cost (Personnel) For This Work/Task |  |  |  | 999.35
Work/Task # & Name: |  | 3.4.2 Integrate with payment gateways(5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Database Engineer | 1 | 5 | 199.87 | 999.35
| Total Cost (Personnel) For This Work/Task |  |  |  | 999.35
Work/Task # & Name: |  | 3.4.3 Integrate with email marketing platforms(5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Database Engineer | 1 | 5 | 199.87 | 999.35
| Total Cost (Personnel) For This Work/Task |  |  |  | 999.35
Work/Task # & Name: |  | 3.5.1 Functionality testing(5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Software Tester | 1 | 5 | 225 | 1125
| Total Cost (Personnel) For This Work/Task |  |  |  | 1125
Work/Task # & Name: |  | 3.5.2 User acceptance testing(7Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Software Tester | 1 | 7 | 225 | 1575
| Total Cost (Personnel) For This Work/Task |  |  |  | 1575
Work/Task # & Name: |  | 3.5.3 Performance testing(3Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Software Tester | 1 | 3 | 225 | 675
| Total Cost (Personnel) For This Work/Task |  |  |  | 675
4. CONTROL & MONITORING
Work/Task # & Name: |  | 4.2.1 Monitor risks( 5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 5 | 306.67 | 1533.35
2 | System Analyst | 1 | 5 | 183.33 | 916.65
| Total Cost (Personnel) For This Work/Task |  |  |  | 2450
Work/Task # & Name: |  | 4.2.2 Implement mitigation plans( 5Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 5 | 306.67 | 1533.35
2 | System Analyst | 1 | 5 | 183.33 | 916.65
| Total Cost (Personnel) For This Work/Task |  |  |  | 2450
Work/Task # & Name: |  | 4.3.1 Provide training resources(3Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | System Analyst | 1 | 3 | 183.33 | 549.99
| Total Cost (Personnel) For This Work/Task |  |  |  | 549.99
Work/Task # & Name: |  | 4.3.2 Offer helpdesk support(2Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | System Analyst | 1 | 2 | 183.33 | 366.66
| Total Cost (Personnel) For This Work/Task |  |  |  | 366.66
5. CLOSING
Work/Task # & Name: |  | 5.1.1 Finalize documentation( 2Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 2 | 306.67 | 613.34
2 | System Analyst | 1 | 2 | 183.33 | 366.66
| Total Cost (Personnel) For This Work/Task |  |  |  | 980
Work/Task # & Name: |  | 5.1.2 Handover to client ( 1Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 1 | 306.67 | 306.67
2 | System Analyst | 1 | 1 | 183.33 | 183.33
| Total Cost (Personnel) For This Work/Task |  |  |  | 490
Work/Task # & Name: |  | 5.2.1 Review project outcomes ( 3Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 3 | 306.67 | 920.01
2 | System Analyst | 1 | 2 | 183.33 | 366.66
| Total Cost (Personnel) For This Work/Task |  |  |  | 1286.67
Work/Task # & Name: |  | 5.2.2 Document lessons learned ( 1Days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Project Manager | 1 | 1 | 306.67 | 306.67
2 | System Analyst | 1 | 1 | 183.33 | 183.33
| Total Cost (Personnel) For This Work/Task |  |  |  | 490