## PROJECT COST
Level-1 | Level-2 | Level-3 | Level-4
ABC MANAGEMENT SYSTEM |  |  | 1.1.1 Visit XYZ Site office
1339
1.1.2 Gather Requirememt
0
1.1.3 Identify Objective
0
|  | 1.1 Create Project Charter | 1.1.4 Identify Scope
|  | 1500 | 0
1.1.5 Work X
61
| 1. INITIATION |  | 1.1.6 Work Y
| 2500 |  | 0
1.1.7 Work Z
100
1.1 Identify Stakeholder
0
1.1 Identify Stakeholder
|  | 1000 | 1.1 Intervew the Developers/Experts
1000

## Man
Work/Task # & Name: |  | 1.1 Project Planning (8 days) | [5 empty] | salary
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) |  | project manager | 156.52
1 | project manager | 1 | 2 | 156.52 | 313.04 |  | ui/ux desinger | 96.77
2 | business analyst | 1 | 2 | 103.23 | 206.46 |  | technical lead | 112.9
3 | system analyst | 1 | 2 | 93.55 | 187.1 |  | software engineer | 129.03
4 | business analyst | 1 | 2 | 103.23 | 206.46 |  | QA engineer | 122.58
| Total Cost (Personnel) For This Work/Task |  |  |  | 913.06 | 913.06 | tester | 122.58
[7 empty] | system analyst | 93.55
Work/Task # & Name: |  | 1.2 Resource Allocation(5days) |  |  |  |  | business analyst | 103.23
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM) |  | database architect | 161.29
1 | project manager | 1 | 1 | 156.52 | 156.52
2 | technical lead | 1 | 2 | 112.9 | 225.8
3 | business analyst | 1 | 1 | 103.23 | 103.23
4 | software engineer | 1 | 1 | 129.03 | 129.03
5 | QA engineer | 1 | 1 | 122.58 | 122.58
| Total Cost (Personnel) For This Work/Task |  |  |  | 737.16 | 737.16
Work/Task # & Name: |  | 1.3 Budgeting (5 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | project manager | 1 | 1 | 156.52 | 156.52
2 | business analyst | 1 | 2 | 103.23 | 206.46
3 | system analyst | 1 | 1 | 93.55 | 93.55
4 | technical lead | 1 | 1 | 112.9 | 112.9
| Total Cost (Personnel) For This Work/Task |  |  |  | 569.43 | 569.43
Work/Task # & Name: |  | 2.1 Stakeholder Interview(5 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | project manager | 1 | 1 | 156.52 | 156.52
2 | business analyst | 1 | 2 | 103.23 | 206.46
3 | system analyst | 1 | 1 | 93.55 | 93.55
4 | ui/ux desinger | 1 | 1 | 96.77 | 96.77
| Total Cost (Personnel) For This Work/Task |  |  |  | 553.3 | 553.3
Work/Task # & Name: |  | 2.2 Requirement Specification (8 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | business analyst | 1 | 3 | 103.23 | 309.69
2 | system analyst | 1 | 1 | 93.55 | 93.55
3 | technical lead | 1 | 2 | 112.9 | 225.8
4 | ui/ux desinger | 1 | 2 | 96.77 | 193.54
| Total Cost (Personnel) For This Work/Task |  |  |  | 822.58 | 822.58
Work/Task # & Name: |  | 2.3 Documentation (7 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | project manager | 1 | 1 | 156.52 | 156.52
2 | business analyst | 1 | 2 | 103.23 | 206.46
3 | system analyst | 1 | 2 | 93.55 | 187.1
4 | ui/ux desinger | 1 | 2 | 96.77 | 193.54
| Total Cost (Personnel) For This Work/Task |  |  |  | 743.62 | 743.62
Work/Task # & Name: |  | 3.1 Architecture Design (7 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | technical lead | 1 | 2 | 112.9 | 225.8
2 | system analyst | 1 | 1 | 93.55 | 93.55
3 | software engineer | 1 | 2 | 129.03 | 258.06
4 | project manager | 1 | 2 | 156.52 | 313.04
| Total Cost (Personnel) For This Work/Task |  |  |  | 890.45 | 890.45
Work/Task # & Name: |  | 3.2 Database Design (6 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | database architect | 1 | 2 | 161.29 | 322.58
2 | system analyst | 1 | 1 | 93.55 | 93.55
3 | software engineer | 1 | 2 | 129.03 | 258.06
4 | project manager | 1 | 1 | 156.52 | 156.52
| Total Cost (Personnel) For This Work/Task |  |  |  | 830.71 | 830.71
Work/Task # & Name: |  | 3.3 User Interface Design (9 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | ui/ux desinger | 1 | 3 | 96.77 | 290.31
2 | business analyst | 1 | 2 | 103.23 | 206.46
3 | software engineer | 1 | 3 | 129.03 | 387.09
4 | project manager | 1 | 1 | 156.52 | 156.52
| Total Cost (Personnel) For This Work/Task |  |  |  | 1040.38 | 1040.38
Work/Task # & Name: |  | 4.1 Environment Setup (5 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | technical lead | 1 | 3 | 112.9 | 338.7
2 | system analyst | 1 | 2 | 93.55 | 187.1
3 | software engineer | 1 | 3 | 129.03 | 387.09
4 | QA engineer | 1 | 1 | 122.58 | 122.58
5 | project manager | 1 | 5 | 156.52 | 782.6
| Total Cost (Personnel) For This Work/Task |  |  |  | 1818.07 | 1818.07
Work/Task # & Name: |  | 4.2 Coding (20 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | software engineer | 1 | 12 | 129.03 | 1548.36
2 | technical lead | 1 | 4 | 112.9 | 451.6
3 | system analyst | 1 | 2 | 93.55 | 187.1
4 | project manager | 1 | 20 | 156.52 | 3130.4
| Total Cost (Personnel) For This Work/Task |  |  |  | 5317.46 | 5317.46
Work/Task # & Name: |  | 4.3 Integration (5 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | technical lead | 1 | 1 | 112.9 | 112.9
2 | software engineer | 1 | 2 | 129.03 | 258.06
3 | QA engineer | 1 | 1 | 122.58 | 122.58
4 | system analyst | 1 | 1 | 93.55 | 93.55
5 | project manager | 1 | 5 | 156.52 | 782.6
| Total Cost (Personnel) For This Work/Task |  |  |  | 1369.69 | 1369.69
Work/Task # & Name: |  | 5.1 System Testing (10 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | QA engineer | 1 | 3 | 122.58 | 367.74
2 | software engineer | 1 | 3 | 129.03 | 387.09
3 | technical lead | 1 | 2 | 112.9 | 225.8
4 | system analyst | 1 | 1 | 93.55 | 93.55
5 | project manager | 1 | 10 | 156.52 | 1565.2
| Total Cost (Personnel) For This Work/Task |  |  |  | 2639.38 | 2639.38
Work/Task # & Name: |  | 5.2 User Acceptance Test (11 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | Business Analyst | 1 | 4 | 103.23 | 412.92
2 | QA engineer | 1 | 2 | 122.58 | 245.16
3 | software engineer | 1 | 2 | 129.03 | 258.06
4 | project manager | 1 | 11 | 156.52 | 1721.72
| Total Cost (Personnel) For This Work/Task |  |  |  | 2637.86 | 2637.86
Work/Task # & Name: |  | 5.3 Bug Fixing (4 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | software engineer | 1 | 2 | 129.03 | 258.06
2 | QA engineer | 1 | 1 | 122.58 | 122.58
3 | technical lead | 1 | 1 | 112.9 | 112.9
4 | project manager | 1 | 4 | 156.52 | 626.08
| Total Cost (Personnel) For This Work/Task |  |  |  | 1119.62 | 1119.62
Work/Task # & Name: |  | 6.1 Bug Tracking and Fixes (14 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | software engineer | 1 | 5 | 129.03 | 645.15
2 | QA engineer | 1 | 3 | 122.58 | 367.74
3 | technical lead | 1 | 2 | 112.9 | 225.8
4 | project manager | 1 | 14 | 156.52 | 2191.28
| Total Cost (Personnel) For This Work/Task |  |  |  | 3429.97 | 3429.97
Work/Task # & Name: |  | 6.2 Update Release (58 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | software engineer | 1 | 10 | 129.03 | 1290.3
2 | QA engineer | 1 | 15 | 122.58 | 1838.7
3 | technical lead | 1 | 5 | 112.9 | 564.5
4 | project manager | 1 | 58 | 156.52 | 9078.16
| Total Cost (Personnel) For This Work/Task |  |  |  | 12771.66 | 12771.66
Work/Task # & Name: |  | 6.3 Documentation Updates (22 days)
No | Person Involved (PI) | No of PI | Total Day(s) Involve | Rate/Day (RM) | Total by Individual PI (RM)
1 | system analyst | 1 | 8 | 93.55 | 748.4
2 | software engineer | 1 | 5 | 129.03 | 645.15
3 | business analyst | 1 | 4 | 103.23 | 412.92
4 | project manager | 1 | 22 | 156.52 | 3443.44
| Total Cost (Personnel) For This Work/Task |  |  |  | 5249.91 | 5249.91
| Total Cost (Personnel) For This Project |  |  |  |  | 43454.31

## Machine (Tools, Logistic, etc)
Work/Task # & Name: |  | 1.1 Project Planning (8 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 4 |  | 3 |  | 12 |  | assesories | 3
2 | A4 paper |  | 1 |  | 14.5 |  | 14.5 |  | A4 paper | 14.5
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0 |  | yearly ASANA liscense | 240
4 | developer PC |  | 0 |  | 2000 |  | 0 |  | developer PC | 2000
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0 |  | yearly MS office liscense | 1200
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0 |  | yearly adobe liscense | 2040
7 | yearly internet access |  | 0 |  | 250 |  | 0 |  | yearly internet access | 250
8 | TnT claim per person | 4 |  | 8 |  | 10 | 320 |  | TnT claim per person | 10
9 | meal with customer | 4 |  | 7 |  | 20 | 560 |  | meal with customer | 20
| Total Cost (Machine) For This Work/Task | [5 empty] | 906.5 | 906.5
Work/Task # & Name: |  | 1.2 Resource Allocation(5days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 4 |  | 3 |  | 12
2 | A4 paper |  | 0 |  | 14.5 |  | 0
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 5 |  | 5 |  | 10 | 250
9 | meal with customer | 5 |  | 5 |  | 20 | 500
| Total Cost (Machine) For This Work/Task | [5 empty] | 762 | 762
Work/Task # & Name: |  | 1.3 Budgeting (5 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 2 |  | 3 |  | 6
2 | A4 paper |  | 1 |  | 14.5 |  | 14.5
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 5 |  | 10 | 200
9 | meal with customer | 4 |  | 5 |  | 20 | 400
| Total Cost (Machine) For This Work/Task | [5 empty] | 620.5 | 620.5
Work/Task # & Name: |  | 2.1 Stakeholder Interview(5 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 2 |  | 3 |  | 6
2 | A4 paper |  | 1 |  | 14.5 |  | 14.5
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 5 |  | 10 | 200
9 | meal with customer | 4 |  | 5 |  | 20 | 400
| Total Cost (Machine) For This Work/Task | [5 empty] | 620.5 | 620.5
Work/Task # & Name: |  | 2.2 Requirement Specification (8 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 2 |  | 3 |  | 6
2 | A4 paper |  | 1 |  | 14.5 |  | 14.5
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 4 |  | 10 | 160
9 | meal with customer | 4 |  | 4 |  | 20 | 320
| Total Cost (Machine) For This Work/Task | [5 empty] | 500.5 | 500.5
Work/Task # & Name: |  | 2.3 Documentation (7 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 5 |  | 3 |  | 15
2 | A4 paper |  | 4 |  | 14.5 |  | 58
3 | yearly ASANA liscense |  | 1 |  | 240 |  | 240
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 1 |  | 1200 |  | 1200
6 | yearly adobe liscense |  | 1 |  | 2040 |  | 2040
7 | yearly internet access |  | 1 |  | 250 |  | 250
8 | TnT claim per person | 4 |  | 4 |  | 10 | 160
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 3963 | 3963
Work/Task # & Name: |  | 3.1 Architecture Design (7 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 5 |  | 3 |  | 15
2 | A4 paper |  | 2 |  | 14.5 |  | 29
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 7 |  | 10 | 280
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 324 | 324
Work/Task # & Name: |  | 3.2 Database Design (6 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 5 |  | 3 |  | 15
2 | A4 paper |  | 2 |  | 14.5 |  | 29
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 5 |  | 10 | 200
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 244 | 244
Work/Task # & Name: |  | 3.3 User Interface Design (9 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 4 |  | 3 |  | 12
2 | A4 paper |  | 2 |  | 14.5 |  | 29
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 5 |  | 10 | 200
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 241 | 241
Work/Task # & Name: |  | 4.1 Environment Setup (5 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 0 |  | 3 |  | 0
2 | A4 paper |  | 0 |  | 14.5 |  | 0
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 5 |  | 2000 |  | 10000
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 5 |  | 3 |  | 10 | 150
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 10150 | 10150
Work/Task # & Name: |  | 4.2 Coding (20 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 2 |  | 3 |  | 6
2 | A4 paper |  | 0 |  | 14.5 |  | 0
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 10 |  | 10 | 400
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 406 | 406
Work/Task # & Name: |  | 4.3 Integration (5 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 0 |  | 3 |  | 0
2 | A4 paper |  | 0 |  | 14.5 |  | 0
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 5 |  | 10 |  | 10 | 500
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 500 | 500
Work/Task # & Name: |  | 5.1 System Testing (10 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 2 |  | 3 |  | 6
2 | A4 paper |  | 1 |  | 14.5 |  | 14.5
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 5 |  | 5 |  | 10 | 250
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 270.5 | 270.5
Work/Task # & Name: |  | 5.2 User Acceptance Test (11 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 0 |  | 3 |  | 0
2 | A4 paper |  | 0 |  | 14.5 |  | 0
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 5 |  | 10 | 200
9 | meal with customer | 2 |  | 5 |  | 20 | 200
| Total Cost (Machine) For This Work/Task | [5 empty] | 400 | 400
Work/Task # & Name: |  | 5.3 Bug Fixing (4 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 0 |  | 3 |  | 0
2 | A4 paper |  | 0 |  | 14.5 |  | 0
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 3 |  | 10 | 120
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 120 | 120
Work/Task # & Name: |  | 6.1 Bug Tracking and Fixes (14 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 0 |  | 3 |  | 0
2 | A4 paper |  | 0 |  | 14.5 |  | 0
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 6 |  | 10 | 240
9 | meal with customer | 0 |  | 0 |  | 20 | 0
| Total Cost (Machine) For This Work/Task | [5 empty] | 240 | 240
Work/Task # & Name: |  | 6.2 Update Release (58 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 1 |  | 3 |  | 3
2 | A4 paper |  | 1 |  | 14.5 |  | 14.5
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 10 |  | 10 | 400
9 | meal with customer | 2 |  | 10 |  | 20 | 400
| Total Cost (Machine) For This Work/Task | [5 empty] | 817.5 | 817.5
Work/Task # & Name: |  | 6.3 Documentation Updates (22 days)
No | Item | No of PI | No of Item | Total Day(s) Involve | Cost/Item (RM) | Rate/Day (RM) | Total by Individual PI (RM)
1 | assesories |  | 5 |  | 3 |  | 15
2 | A4 paper |  | 2 |  | 14.5 |  | 29
3 | yearly ASANA liscense |  | 0 |  | 240 |  | 0
4 | developer PC |  | 0 |  | 2000 |  | 0
5 | yearly MS office liscense |  | 0 |  | 1200 |  | 0
6 | yearly adobe liscense |  | 0 |  | 2040 |  | 0
7 | yearly internet access |  | 0 |  | 250 |  | 0
8 | TnT claim per person | 4 |  | 10 |  | 10 | 400
9 | meal with customer | 4 |  | 4 |  | 20 | 320
| Total Cost (Machine) For This Work/Task | [5 empty] | 764 | 764
| Total Cost (Machine) For This Project | [6 empty] | 21850